## Slide 1: Chap#28
Risk Management

## Slide 2: Content

## Slide 3: 28.1 REACTIVE VERSUS PROACTIVE RISK STRATEGIES
Reactive strategy monitors the project for likely risks. Resources are set aside to deal with them, should they become actual problems. More commonly, the software team does nothing about risks until something goes wrong. Then, the team flies into action in an attempt to correct the problem rapidly. This is often called a fire-fighting mode.
Proactive strategy begins long before technical work is initiated. Potential risks are identified, their probability and impact are assessed, and they are ranked by importance. Then, the software team establishes a plan for managing risk. The primary objective is to avoid risk, but because not all risks can be avoided, the team works to develop a contingency plan that will enable it to respond in a controlled and effective manner.

## Slide 4: 28.2 SOFTWARE RISKS
Risk always involves two characteristics: uncertainty—the risk may or may not happen; that is, there are no 100 percent probable risks—and loss—if the risk becomes a reality, unwanted consequences or losses will occur. Different categories of risks are considered:
Project risks: threaten the project plan. Project risks become real, it is likely that the project schedule will slip and that costs will increase. Project risks identify potential budgetary, schedule, personnel (staffing and organization), resource, stakeholder, and requirements problems and their impact on a software project.
Technical risks: threaten the quality and timeliness of the software to be produced. If a technical risk becomes a reality, implementation may become difficult or impossible. Technical risks identify potential design, implementation, specification ambiguity, technical Uncertainty,interface, verification, and maintenance problems.

## Slide 5
Business risks threaten the viability(growth, develop) of the software to be built and often jeopardize(risk) the project or the product. Candidates for the top five business risks are (1) building an excellent product or system that no one really wants (market risk), (2) building a product that no longer fits into the overall business strategy for the company (strategic risk), (3) building a product that the sales force doesn’t understand how to sell (sales risk), (4) losing the support of senior management due to a change in focus or a change in people (management risk), and (5) losing budgetary or personnel commitment (budget risks).

## Slide 6: General categorization of risks
Known risks are those that can be uncovered after careful evaluation of the project plan, the business and technical environment in which the project is being developed, and other reliable information sources (e.g., unrealistic delivery date, lack of documented requirements or software scope, poor development environment).
Predictable risks are from past project experience (e.g., staff turnover, poor communication with the customer, dilution of staff effort as ongoing maintenance requests are serviced).
Unpredictable risks They can and do occur, but they are extremely difficult to identify in advance.
Notes: turnover: rotation
Dilution: lesson staff efforts

## Slide 7: 28.3 RISK IDENTIFICATION
Risk identification is a systematic attempt to specify threats to the project plan.By identifying known and predictable risks, the project manager takes a first step toward avoiding them when possible and controlling them when necessary.
Generic risks are a potential threat to every software project. Product-specific risks can be identified only by those with a clear understanding of the technology, the people, and the environment that is specific to the software that is to be built.Predictable risks in the following generic subcategories:
• Product size—risks associated with the overall size of the software to be built or modified.
• Business impact—risks associated with constraints imposed by management or the marketplace.

## Slide 8
• Stakeholder characteristics—risks associated with the sophistication of the stakeholders and the developer’s ability to communicate with stakeholders in a timely manner.
• Process definition—risks associated with the degree to which the software process has been defined and is followed by the development organization.
• Development environment—risks associated with the availability and quality of the tools to be used to build the product.
• Technology to be built—risks associated with the complexity of the system to be built and the “newness” of the technology that is packaged by the system.
• Staff size and experience—risks associated with the overall technical and project experience of the software engineers who will do the work.
Notes: Sophisticated: complex

## Slide 9: 28.3.1 Assessing Overall Project Risk
Top software and customer managers formally committed to support the project
End users enthusiastically committed to the project
Requirements fully understood by the software engineering team and its customers
customers been involved fully in the definition of requirements
end users have realistic expectations
project scope stable
software engineering team have the right mix of skills
project requirements stable
project team have experience with the technology to be implemented
number of people on the project team adequate to do the job
Customer agree on the importance of the project and on the requirements for the system/product to be built

## Slide 10: 28.3.2 Risk Components and Drivers
Risk components are defined in the following manner:
• Performance risk—the degree of uncertainty that the product will meet its requirements and be fit for its intended use.
• Cost risk—the degree of uncertainty that the project budget will be maintained.
• Support risk—the degree of uncertainty that the resultant software will be easy to correct, adapt, and enhance.
• Schedule risk—the degree of uncertainty that the project schedule will be maintained and that the product will be delivered on time.

## Slide 11: 28.4 RISK PROJECTION
Risk projection, also called risk estimation, attempts to rate each risk in two ways—(1) the probability that the risk is real and (2) the consequences of the problems associated with the risk, should it occur. You work along with other managers and technical staff to perform four risk projection steps:
1. Establish a scale that reflects the perceived likelihood of a risk.
2. Delineate(describe) the consequences of the risk.
3. Estimate the impact of the risk on the project and the product.
4. Assess the overall accuracy of the risk projection so that there will be no misunderstandings.

## Slide 12
28.4.1 Developing a Risk Table
A risk table provides you with a simple technique for risk projection
You begin by listing all risks in the first column of the table. This can be accomplished with the help of the risk item checklists.
The cutoff line implies that only risks that lie above the line will be given further attention. Risks that fall below the line are reevaluated to accomplish second-order prioritization.
Risk drivers can be assessed on a qualitative probability scale that has the following values: impossible, improbable(doubt), probable(likely to happen), and frequent(rare).
Tables from book

## Slide 13
28.4.2 Assessing Risk Impact
Three factors affect the consequences that are likely if a risk does occur: its nature, its scope, and its timing.
The overall risk exposure RE is determined using the following relationship RE= P x C where P is the probability of occurrence for a risk, and C is the cost to the project should the risk occur.
Risk identification, Risk probability(80%), Risk impact, Risk exposure
Notes: Risk exposure : for adjusting the final cost estimate for a project

## Slide 14: 28.5 RISK REFINEMENT
As time passes and more is learned about the project and the risk, it may be possible to refine the risk into a set of more detailed risks, each somewhat easier to mitigate, monitor,and manage.
One way to do this is to represent the risk in condition-transition-consequence (CTC) format.
Refinement helps to isolate the underlying risks and might lead to easier analysis and response.

## Slide 15: 28.6 RISK MITIGATION, MONITORING, AND MANAGEMENT
Effective strategy must consider three issues: risk avoidance, risk monitoring, and risk management and contingency(condition) planning.
To mitigate this risk, you would develop a strategy for reducing turnover. Among the possible steps to be taken are:
• Meet with current staff to determine causes for turnover(reasons)
• Mitigate those causes that are under your control before starting
develop techniques to handles issues to ensure continuity
Organize project teams so that information about each development activity is widely dispersed.
• Define work product standards and establish mechanisms to be sure that all models and documents are developed in a timely manner.
• Conduct peer reviews of all work
• Assign a backup staff member for every critical technologist
Notes: If hazards can be identified early in the software engineering process, software design features can be specified that will either eliminate or control potential hazards.

## Slide 16: 28.7 THE RMMM PLAN
A risk management strategy can be included in the software project plan, or the risk management steps can be organized into a separate risk mitigation, monitoring, and management plan (RMMM).
Each risk is documented individually using a risk information sheet (RIS) . In most cases, the RIS is maintained using a database system so that creation and information entry, priority ordering, searches, and other analysis may be accomplished easily.
Risk mitigation is a problem avoidance activity. Risk monitoring is a project tracking activity with three primary objectives: (1) to assess whether predicted risks do, in fact, occur; (2) to ensure that risk aversion steps defined for the risk are being properly applied; and (3) to collect information that can be used for future risk analysis.
In many cases, the problems that occur during a project can be traced to more than one risk. Another job of risk monitoring is to attempt to allocate origin [what risk(s) caused which problems throughout the project].
Table from book